## Wildfires
Wildfires Statement of Work
| Project Title |  | Start Date
| Degree Works |  | 2025-11-09 |  |  | Project Duration
| Project Development Team |  | End Date |  |  | in days
| Brandon (SWE), Darion (Designer), Kelly (Tester), Qadir (Lead) |  | 2025-12-01 |  |  | 23
| User Story # | Status | Use Cases | Start Date | End Date | Duration (in days) | Comments | Status
| Brandon |  |  | 2025-11-17 | 2025-12-08 | 22 |  | Not Started
| # Create Student class and used it in the driver | On Hold | SHA 1d4e8e2 | 2025-11-17 | 2025-11-17 | 1 | What is this use case's user story number? If no user story, make sure you add this as a user story in our final sprint. | In Progress
Complete
On Hold
Nov 26th: 8 commits, +257, -11
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| Darion |  |  | 2025-11-22 | 2025-12-08 | 17
Oh no, Assignment08's 700 points is a third of all points this semester and you have no commits!
Nov 26th: 0 commits
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| Kelly |  |  | 2025-11-22 | 2025-12-08 | 17
| Create Professor class and use it in the driver | Complete | SHA baf6ba7,eb73790, 88caab8, bf38652, 75c5089, 8b4132b | 2025-12-01 | 2025-12-01 | 1 | Oh no, Assignment08's 700 points is a third of all points this semester and you have no commits!
| Agile board (user stories and use cases) | Complete | SHA c7b31a2 | 2025-12-01 | 2025-12-01
| product backlog | Complete | SHA baf6ba7, eb73790, 88caab8, 6cacf03, 9b242c9, 7011e4d, c7b31a2, b22706a | 2025-12-01 | 2025-12-01
| Edit Student class to implement Professor class #13 | Complete | SHA baf6ba7, eb73790, 88caab8, bf38652, 75c508, 8b4132b, 95c95f0, 4121080 | 2025-12-01 | 2025-12-01
Nov 26th: 0 commits
| Evaluate Dr. Edwards via Class Climate | Complete |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | On Hold |  | 2025-12-01 | 2025-12-01 | 1
| Qadir |  |  | 2025-11-12 | 2025-12-08 | 27
| # Update README with prioritized projects | Complete | SHA 1976f86, eaeaa3b, 2515e23 | 2025-11-12 | 2025-11-12 | 27 | What is this use case's user story number? If no user story, make sure you add this as a user story in our final sprint.
| Revise project list and descriptions in README | Complete |  | 2025-11-12 | 2025-11-12 | 27
| Added Trello Link to README | Complete |  | 2025-11-12 | 2025-11-12
| Added SDD doc | Complete |  | 2025-11-12 | 2025-11-12
| Added .gitignore, driver.py | Complete |  | 2025-11-13 | 2025-11-13 | 26
| Added transcript class | Complete |  | 2025-11-13 | 2025-11-15 | 23
| Check on the group access to repo | Complete |  | 2025-11-16 | 2025-11-17 | 20
| Update final release and add CLI instructions | Complete |  | 2025-12-01 | 2025-12-01 | 0
Nov 26th: 8 commits, +81, -5
| Evaluate Dr. Edwards via Class Climate | Complete |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Complete |  | 2025-12-01 | 2025-12-01 | 1
Formulas:
Start Date = MIN([Start Date, row below]:F21)
End Date = MAX([End Date, row below]:G21)

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.
https://www.smartsheet.com/top-project-management-excel-templates?srsltid=AfmBOorM8KTqo0GkEazFKhVFp3ozfOh-BifeI1KKxQxM0WpR5p08gBRL