## Wildfires
Wildfires Statement of Work
| Project Title |  | Start Date
| Degree Works |  | 2025-11-09 |  |  | Project Duration
| Project Development Team |  | End Date |  |  | in days
| Brandon (SWE), Darion (Designer), Kelly (Tester), Qadir (Lead) |  | 2025-12-01 |  |  | 23
| User Story # | Status | Use Cases | Start Date | End Date | Duration (in days) | Comments | Status
| Brandon |  |  | 2025-11-17 | 2025-12-08 | 22 |  | Not Started
| # Create Student class and used it in the driver User Story #2 | Complete | SHA 1d4e8e2 | 2025-11-17 | 2025-11-17 | 1 | What is this use case's user story number? If no user story, make sure you add this as a user story in our final sprint. | In Progress
| (Create a advisor Class) User Story # was removed from backlog | Complete | SHA 3a281f3 | 2025-11-17 | 2025-11-18 |  |  | Complete
| (Create a Login Class) #12 | Complete | SHA 4d1fdcb, SHA 11c53fe , SHA f4d3084, SHA a407ee6, SHA 849d6af, SHA 60387d4 | 2025-11-24 | 2025-11-24 |  |  | On Hold
Nov 26th: 8 commits, +257, -11
| Evaluate Dr. Edwards via Class Climate | Complete |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Complete |  | 2025-12-01 | 2025-12-01 | 1
| Darion |  |  | 2025-11-22 | 2025-12-08 | 17
Oh no, Assignment08's 700 points is a third of all points this semester and you have no commits!
Nov 26th: 0 commits
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| Kelly |  |  | 2025-11-22 | 2025-12-08 | 17
Oh no, Assignment08's 700 points is a third of all points this semester and you have no commits!
Nov 26th: 0 commits
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| Qadir |  |  | 2025-11-12 | 2025-12-08 | 27
| # Update README with prioritized projects | Complete | SHA 1976f86, eaeaa3b, 2515e23 | 2025-11-12 | 2025-11-12 |  | What is this use case's user story number? If no user story, make sure you add this as a user story in our final sprint.
|  | Complete |  | 2025-11-12
|  | Complete |  | 2025-11-12
|  | Complete |  | 2025-11-12
Nov 26th: 8 commits, +81, -5
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
Formulas:
Start Date = MIN([Start Date, row below]:F21)
End Date = MAX([End Date, row below]:G21)

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.
https://www.smartsheet.com/top-project-management-excel-templates?srsltid=AfmBOorM8KTqo0GkEazFKhVFp3ozfOh-BifeI1KKxQxM0WpR5p08gBRL