## Wildfires
Wildfires Statement of Work
| Project Title |  | Start Date
| Degree Works |  | 2025-11-09 |  |  | Project Duration
| Project Development Team |  | End Date |  |  | in days
| Brandon (SWE), Darion (Designer), Kelly (Tester), Qadir (Lead) |  | 2025-12-01 |  |  | 23
| User Story # | Status | Use Cases | Start Date | End Date | Duration (in days) | Comments
| Brandon |  |  | 2025-11-17 | 2025-12-08 | 22
edit main | #2 Create Student class and used it in the driver User Story | Complete | SHA 1d4e8e2 | 2025-11-17 | 2025-11-17 | 1
Advisor (_ensure_gpa, student_below_gpa, build_alert, scan_students, print_alerts) and calls in main | (Create a advisor Class) User Story # was removed from backlog | Complete | SHA 3a281f3 | 2025-11-17 | 2025-11-18 | 2
Role User LoginManager (__init__) _hash_password, _check_password, add_user, authenticate, get_role, is_advisor, is_teacher, is_student, list_users updated driver | #12 (Create a Login Class) | Complete | SHA 4d1fdcb, SHA 11c53fe , SHA f4d3084, SHA a407ee6, SHA 849d6af, SHA 60387d4 | 2025-11-24 | 2025-11-24 | 1
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| Darion |  |  | 2025-11-22 | 2025-12-08 | 17
UML_class_diagram.png | #10, Create UML | Complete | 820976f51aeb807bc836e7e73169fb80f5ba7adc | 2025-11-22 | 2025-11-30
Degree_Works_mockup.png, Transcript_upload-mockup.png | #13, Create Degree Works mockup site | Complete | 6b66d002d6964dba411f342de04163c4d858237b | 2025-11-28 | 2025-12-01
Darion, did you only create pictures and leave the project development to everyone else? This is fine if the project works exactly as your UML shows. Does it?
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| Kelly |  |  | 2025-11-22 | 2025-12-08 | 17
backup doc, Professor (__init__, enter_midterm_grade, enter_final_grade, view_transcript), edit driver | Create Professor class and use it in the driver | Complete | SHA baf6ba7,eb73790, 88caab8, bf38652, 75c5089, 8b4132b | 2025-12-01 | 2025-12-01 | 1
updated docs | Agile board (user stories and use cases) | Complete | SHA c7b31a2 | 2025-12-01 | 2025-12-01 | 1
See Row 29. check. Updated docs | product backlog | Complete | SHA baf6ba7, eb73790, 88caab8, 6cacf03, 9b242c9, 7011e4d, c7b31a2, b22706a | 2025-12-01 | 2025-12-01 | 1
See Row 29. Student (set_midterm_grade, set_final)grade, get_transcript) and calls | Edit Student class to implement Professor class #13 | Complete | SHA baf6ba7, eb73790, 88caab8, bf38652, 75c508, 8b4132b, 95c95f0, 4121080 | 2025-12-01 | 2025-12-01 | 1
| Evaluate Dr. Edwards via Class Climate | Complete |  | 2025-11-22 | 2025-12-08 | 1
| Evaluate team using Brightspace survey | On Hold |  | 2025-12-01 | 2025-12-01 | 1
| Qadir |  |  | 2025-11-12 | 2025-12-08 | 27
README | Update README with prioritized projects | Complete | SHA 1976f86, eaeaa3b, 2515e23 | 2025-11-12 | 2025-11-12 | 1
more edits of README | Revise project list and descriptions in README, Added Trello Link to README | Complete | SHA 1976f86, eaeaa3b | 2025-11-12 | 2025-11-12 | 1
SDD | Added SDD doc | Complete | SHA e81500d | 2025-11-12 | 2025-11-12 | 1
.gitignore | Added .gitignore, driver.py | Complete | SHA 420bfd3 | 2025-11-13 | 2025-11-13 | 1
more edits of SDD | Added transcript class | Complete | SHA 007c65a | 2025-11-13 | 2025-11-15 | 2
Transcript (__init__, display, calculate_gpa) | Check on the group access to repo | Complete | SHA b45d2d7 | 2025-11-16 | 2025-11-17 | 2
display_classes_taken | Update final release and add CLI instructions | Complete | SHA 26b549c | 2025-12-01 | 2025-12-01 | 1
more edits of SDD, called Student methods, see Row 10, see Row 11, see Row 15, check | Merge teammate branches | Complete | SHA 58da2e2, 4e2d96d, 0dc5b11, 1aff78a, f1cd8ba, 836f9df | 2025-11-15 | 2025-12-01 | 18
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
Formulas:
Start Date = MIN([Start Date, row below]:F13)
End Date = MAX([End Date, row below]:G13)

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.
https://www.smartsheet.com/top-project-management-excel-templates?srsltid=AfmBOorM8KTqo0GkEazFKhVFp3ozfOh-BifeI1KKxQxM0WpR5p08gBRL